## Detalhes do Projeto
Dollar
Detalhes do Projeto
Código do Projeto | P01
Nome do Projeto | Sistema de cotação para transportadora
Ordem de Trabalho | 1
Linguagem | Java
Cliente | Academia
Data de início | 2022-09-09
Data de Término | 2019-04-12
Resumo da Planilha | FPA | IFPUG FPA
Contagem de PF | 38.1963 | 47
Reuso de PFs | 0 | 0
Processos de PFs | 2.4
Horas Homem Estimadas | 162.3853
Custo Total | 4059.6316
Resumo de APF | Resumo de IFPUG APF
ANÁLISE DE PONTOS DE FUNÇÃO

## Casos de Uso
Referencia ID | Descrição | Dias Homem | UFP | Reuso FP
1 | Solicitar Cotação | 5.46 | 10.92 | 0
2 | Aprovar Cotação | 4.875 | 9.75 | 0
3 | Sistema de lançamento de coletas | 5.1 | 10.2 | 0
4 | Rastreamento do transporte | 4.8632 | 9.7263 | 0
5 | Finalização e roteirização das entregas | 0 | 0 | 0
6 | Sistema de entrega e comprovantes de entrega | 0 | 0 | 0
HISTÓRIAS DO USUÁRIO/CASOS DE USO

## Reuso
AAF (fator de ajuste da adaptação - AAF =.4 Modificações de Design x.3 MOdificações no Código x.3 Teste e Integração) |  |  | Modificação Solicitada
Referencia ID | Descrição | Contagem de FP | Projeto | Código | Teste & Integração | Reutilização FP | Homem Hora Refatoração | Referencia do Projeto
|  | 0 | 0% | 0% | 0%
Nota
Para integração e reutilização de componentes, não inclua como função de dados ou função de transação, use somente a contagem PF não ajustada da planilha PF original para os componentes mencionados acima, isso será adicionado à contagem PF de reutilização. Para informações adicionais, consulte: http://www.ifpug.org/Conference%20Proceedings/IFPUG-2004/IFPUG2004-31-Roetzheim-estimating-softwre-reuse-equivalietn-function-points.pdf
APLICAÇÕES REUTILIZÁVEIS/COMPONENTES

## Funções Dados
Novos PF Não Ajustados, PF Progressivos, Contagem IPF
Arquivos Lógicos | Referência ID | [9 empty] | ILF/EIF | DET | RET | PET | LCS | Horas Homem | UFP | UPFP | IPF |  |  |  |  | Reuso (Y/N) | Reuso % | PF Reuso | DET Detalhes | RET Detalhes | PET Detalhes | LCS Detalhes | Detalhes de reuso
Freelancer | 2 | [9 empty] | ILF | 25 | 1 | 0 | 2 | 14 | 7 | 3.5 | 0
Cliente | 1 | [9 empty] | ILF | 28 | 1 | 0 | 2 | 15.68 | 7 | 3.92 | 0
Serviço | 3 | [9 empty] | ILF | 20 | 2 | 1 | 3 | 18.4 | 10 | 4 | 0.6
Proposta | 4 | [9 empty] | ILF | 15 | 2 | 1 | 2 | 24.5053 | 7 | 5.5263 | 0.6
[16 empty] | 72.5853 | 31 | 16.9463 | 1.2 | [6 empty] | 0
|  | PF Não Ajustados, PF Progressivos, Pré Contagem IPF | [8 empty] | PF Não Ajustados, PF Progressivos, Pós Contagem IPF
Logical Files | Referencia ID | ILF/EIF | DET | RET | PET | LCS | Horas Homem | UFP | UPFP | IPF | ILF/EIF | DET | RET | PET | LCS | Horas Homem | UFP | UPFP | IPF | Impacto DET | Impacto RET | Impacto PET | Impacto LCS | Reuso (Y/N) | Reuso % | PF Reuso | DET Detalhes | RET Detalhes | PET Detalhes | LCS Detalhes | Detalhes de reuso
[7 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Contagem de PF Não Ajustados + Pós Contagem de IPF antes da Exclusão
Arquivos Lógicos | Referencia ID | [9 empty] | ILF/EIF | DET | RET | PET | LCS | Horas Homem | UFP | UPFP | IPF | [7 empty] | Detalhes DET | Detalhes RET | Detalhes PET | Detalhes LCS
[16 empty] | 0 | 0 | 0 | 0
Resumo de PFA Progressivo
|  |  |  | Adicionados | Modificados | Excluídos | Reuso
|  |  | Contagem ILF | 18.1463 | 0 | 0 | 0
|  |  | Contagem EIF | 0 | 0 | 0 | 0
|  |  | Horas Homem | 72.5853 | 0 | 0
|  |  | Total de PF Adicionados |  |  | 18.1463 | 0
|  |  | Total de PF Modificados |  |  | 0 | 0
|  |  | Total de PF Excluídos |  |  | 0
|  |  | Total de PF Processados |  |  | 1.2
|  |  | Total de PF Reusados |  |  | 0
|  |  | Horas Homem |  |  | 72.5853
Resumo de UFP IFPUG
|  |  | Total de PF Adicionados |  |  | 31
|  |  | Total de PF Modificados |  |  | 0
|  |  | Total de PF Excluídos |  |  | 0
ADICIONADOS
MODIFICADOS
EXCLUÍDOS

## Funções Transações
New Unadjusted Progressive FP Count + Integrated Process Flow Count
Transações | Reference ID | [9 empty] | Type | DET | FTR | PET | LCS | Man Hours | UFP | UPFP | IPF |  |  |  |  | Reuse | Reuse % | Reuse FP | DET Details | FTR Details | PET Details | LCS Details | Reuse Details
Freelancer | 2 | [9 empty] | EI | 25 | 1 | 0 | 2 | 25 | 4 | 6.25 | 0
Cliente | 1 | [9 empty] | EI | 28 | 1 | 0 | 2 | 28 | 4 | 7 | 0
Serviço | 3 | [9 empty] | EO | 20 | 1 | 1 | 3 | 22.4 | 5 | 5 | 0.6
Proposta | 4 | [9 empty] | EI | 15 | 1 | 1 | 2 | 14.4 | 3 | 3 | 0.6
TOTAL | [15 empty] | 89.8 | 16 | 21.25 | 1.2 | [6 empty] | 0
|  | Unadjusted FP, Porgressive FP , IPF Pre Count | [8 empty] | Unadjusted FP Count + IPF Count Post Count
Transactions | Reference ID | Type | DET | FTR | PET | LCS | Man Hours | UFP | UPFP | IPF | Type | DET | FTR | PET | LCS | Man Hours | UFP | UPFP | IPF | DET-Impact | FTR-Impact | PET-Impact | LCS-Impact | Reuse(Y/N) | % | Reuse FP
TOTAL | [6 empty] | 0 | UFP: 0; UPFP: 0; IPF: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Unadjusted FP Count + IPF Count Before Deletion
Transactions | Reference ID | [9 empty] | Type | DET | FTR | PET | LCS | Man Hours | UFP | UPFP | IPF | [7 empty] | DET Details | FTR Details | PET Details | LCS Details
TOTAL | [15 empty] | 0 | 0 | 0 | 0
Progressive FPA Summary
[5 empty] | Added | Changed | Deleted | UFP: Reuse
|  |  |  | EI Count | 16.85 | 0 | 0 | UFP: 0
|  |  |  | EO Count | 5.6 | 0 | 0 | UFP: 0
|  |  |  | EQ Count | 0 | 0 | 0 | UFP: 0
|  |  |  | Man Hours | 89.8 | 0 | 0 | bar: UFP to UPFP
|  |  |  | Total Added FP |  |  | 22.45 | UFP: 0
|  |  |  | Total Changed FP |  |  | 0 | UFP: 0
|  |  |  | Total Deleted FP |  |  | 0 | bar: UFP to UPFP
|  |  |  | Total Process FP |  |  | 1.2 | bar: UFP to UPFP
|  |  |  | Total Reuse FP |  |  | 0 | bar: UFP to UPFP
|  |  |  | Man Hours |  |  | 89.8 | bar: UFP to UPFP
IFPUG UFP Summary
|  |  |  | Total Added FP |  |  | 16
|  |  |  | Total Changed FP |  |  | 0
|  |  |  | Total Deleted FP |  |  | 0
Changed
Deleted
Changed
ADICIONADOS
MODIFICADOS
EXCLUÍDOS

## Indices PF
|  |  | IFPUG FP REFERENCE |  |  |  | Progressive FP Coefficients
| EI - Value Ranges |  |  |  |  | EI - Progressive Index
|  |  | DET |  |  |  | DET
| FTR |  | 1-4 | 5-15 | 16+ | FTR | 1-4 | 5-15 | 16+
| <2 | 1 | 3 | 3 | 4 | 1, 2 | 0.75 | 0.2 | 0.25
| 2 | 2 | 3 | 4 | 6 | 3, 4 | 0.75 | 0.26667 | 0.375
| >2 | 3 | 4 | 6 | 6 | 5, 6 | 1 | 0.4 | 0.375
| Range |  | 5 | 16 | 17 | Range | 5 | 16 | 17
| EQ - Value Ranges |  |  |  |  | EQ - Progressive Index
|  |  | DET |  |  |  | DET
| FTR |  | 1-5 | 6-19 | 20+ | FTR | 1-5 | 6-19 | 20+
| <2 | 1 | 3 | 3 | 4 | 1, 2 | 0.6 | 0.15789 | 0.2
| 2,3 | 3 | 3 | 4 | 6 | 3, 4 | 0.6 | 0.21053 | 0.3
| >3 | 4 | 4 | 6 | 6 | 5, 6 | 0.8 | 0.31579 | 0.3
| Range |  | 6 | 20 | 21 | Range | 6 | 20 | 21
| EO - Value Ranges |  |  |  |  | EO - Progressive Index
|  |  | DET |  |  |  | DET
| FTR |  | 1-5 | 6-19 | 20+ | FTR | 1-5 | 6-19 | 20+
| <2 | 1 | 4 | 4 | 5 | 1, 2 | 0.8 | 0.21053 | 0.25
| 2, 3 | 3 | 4 | 5 | 7 | 3, 4 | 0.8 | 0.26316 | 0.35
| >3 | 4 | 5 | 7 | 7 | 5, 6 | 1 | 0.36842 | 0.35
| Range |  | 6 | 20 | 21 | Range | 6 | 20 | 21
| ILF - Value Ranges |  |  |  |  | ILF - Progressive Index
|  |  | DET |  |  |  | DET
| RET |  | 1-19 | 20-50 | 51+ | RET | 1-19 | 20-50 | 50+
| <2 | 1 | 7 | 7 | 10 | 1,2 | 0.36842 | 0.14 | 0.19608
| 2,5 | 5 | 7 | 10 | 15 | 3,5 | 0.36842 | 0.2 | 0.29412
| >5 | 6 | 10 | 15 | 15 | 6,8 | 0.52632 | 0.3 | 0.29412
| Range |  | 20 | 51 | 52 | Range | 20 | 51 | 52
| EIF - Value Ranges |  |  |  |  | EIF - Progressive Index
|  |  | DET |  |  |  | DET
| RET |  | 1-19 | 20-50 | 51+ | RET | 1-19 | 20-50 | 50+
| <2 | 1 | 5 | 5 | 7 | 1,2 | 0.26316 | 0.1 | 0.13725
| 2,5 | 5 | 5 | 7 | 10 | 3,5 | 0.26316 | 0.14 | 0.19608
| >5 | 6 | 7 | 10 | 10 | 6,8 | 0.36842 | 0.2 | 0.19608
| Range |  | 20 | 51 | 52 | Range | 19 | 50 | 51
| IPF - Value Ranges |  |  |  |  | IPF - Progressive Index
|  |  | PET |  |  |  | DET
| LCS |  | 1-5 | 6-19 | 20+ | LCS | 1-5 | 6-19 | 20+
| <3 | 2 | 3 | 3 | 5 | 1,2 | 0.6 | 0.15789 | 0.25
| 2,5 | 5 | 3 | 5 | 7 | 3,5 | 0.6 | 0.26316 | 0.35
| >5 | 6 | 5 | 7 | 7 | 6,8 | 1 | 0.36842 | 0.35
| Range |  | 6 | 20 | 21 | Range | 6 | 20 | 21
| Currency |  | Dollar | Workbook Customization |  | World Currency appiled to worksheet
| Hours/FP |  | 4 | Effort Estimation |  | Computed Hours per FP
| Cost/FP |  | 100 | Cost Estimation |  | Cost per new FP computed
| Cost/Reuse FP |  | 75 | Reuse Cost |  | Charges for Reused/Integrated components
Please Note
The above clolums are used for FP forumules and estimation, and should not be changed. The values in blue columns are standard IFPUG reference counts. To modify the range factors please edit the values shaded in blue, any other changes could affect the functioning of the FP sheet. By training the sheet over several existing projects and adjusting the value matrix above in the relevant domin, it can be used for project estimation as per CMMi guidelines for KPMG audit. Please contact Ruben Gerad Mathew(rubengerad@gmail.com) for any clarification or changes required in the sheet. Always use the latest sheet from http://soureforge.net/projects/functionpoints.
KINDLY PROVIDE YOUR RATINGS AND FEEDBACK IN SOURCEFORGE.
PROGESSIVE FP MATRIX

## Cálculo PF
* IFPUG Standard
Function Point Calculation
| The following calculations are based on Progressive Function Point Estimations. Counts denoted in *Red represents Standard IFPUG measures. |  |  |  | FP Count | Man Hours | Reuse FP | Process FP
|  |  |  | ADDED functionality | 40.5963 | 162.3853 | 0 | 2.4
|  |  |  | CHANGED functionality | 0 | 0 | 0 | 0
|  |  |  | DELETED functionality | 0 | 0 |  | 0
[5 empty] | 40.5963 | 162.3853 | 0 | 2.4
| For strict evaluation based approved IFPUG standards use the Adjusted FP Count, and add the Reusable Applciation Components count marked in red. |  |  | IFPUG FP Count
FP Count
|  |  |  | ADDED functionality | 47
|  |  |  | CHANGED functionality | 0
|  |  |  | DELETED functionality | 0
|  |  |  | *Unadjusted FP Count | 47
|  |  |  | *Adjusted FP Count | 47
| Reuse and integration of exisiting application or components not counted as part of Data or Transaction Functions. |  |  | Reuse
|  |  |  | *Adaption Adjustment Factor |  |  | 0
|  |  |  | Refactoring Manhours |  |  | 0
|  |  |  | Unadjusted Reuse FP |  |  | 0
| A VAF index of 1.0 is used to disable vaule adjustment factor, to objtain the raw FP count as required in certain industies. |  |  | Vaule Adjustment Factor
|  |  |  | *VAF Index |  |  | 1
|  |  |  | Unadjusted Progressive Function Point Count |  |  | 40.5963
|  |  |  | Adjusted Progressive Function Point Count |  |  | 40.5963
|  |  |  | Adjusted Progressive Reuse FP Count |  |  | 0
Schedule Index based on Adjusted Progressive FP Count
|  |  |  | Man Hours Estimate |  |  | 162.3853
|  |  |  | Man Days Estimate |  |  | 20.2982
| FP Cost = Adjusted FP Count x Cost per FP ReuseFP Cost = Adj ReuseFP Count x Cost per Reuse FP (Integration/Testing effort is calculated for any reuse) |  |  | Cost Index based on Adjusted Progressive FP Count |  |  | Dollar
|  |  |  | Cost based on Adjusted Progressive Function Points |  |  | 4059.6316
|  |  |  | Total Reuse FP Cost |  |  | 0
|  |  |  | Total Project Development Cost |  |  | 4059.6316
| Value | Characteristic | # | Degree of Influence | Value (0-5) | Comments
| 0 | Not Present, No influence | 1 | Data Communications | 0 | The VAF can be adjusted as per project env, by setting the VAF to 1.00 ensures no VAF is applied on the final FP count.
| 1 | Incidental influence | 2 | Distributed Data Processing | 5
| 2 | Moderate influence | 3 | Performance | 0
| 3 | Average influence | 4 | Heavily used configuration | 5
| 4 | Significant influence | 5 | Transaction rate | 0
| 5 | Strong influence throughout | 6 | Online data entry | 5
|  |  | 7 | End-user efficiency | 0
|  |  | 8 | Online update | 5
|  |  | 9 | Complex processing | 0
|  |  | 10 | Reusability | 5
|  |  | 11 | Installation ease | 0
|  |  | 12 | Operational ease | 5
|  |  | 13 | Multiple sites | 0
|  |  | 14 | Facilitate change | 5
|  |  |  | Total | 35
|  |  |  | Value Adjustment Factor (VAF) | 1
Process FP Count has been accounted in the Added, Change & Deleted Functionality in Progressive FP Count Only
Reuse Man Hours & Cost is calculated based on values provided in Progressive FP Count
FP ESTIMATION
VALUE ADJUSTMENT FACTOR (VAF)

## Relatórios
DATA FUNCTIONS - ADDED
Reference | User Story | Function Brief | Type | DET | RET | PET | LCS | IFPUG UFP | Progressive UFP | IPF | Reuse% | Reuse FP | Man Hours | DET Details | RET Details | PET Details | LCS Details | Reuse Details
2 | Aprovar Cotação | Freelancer | ILF | 25 | 1 | 0 | 2 | 7 | 3.5 | 0 |  |  | 14
1 | Solicitar Cotação | Cliente | ILF | 28 | 1 | 0 | 2 | 7 | 3.92 | 0 |  |  | 15.68
3 | Sistema de lançamento de coletas | Serviço | ILF | 20 | 2 | 1 | 3 | 10 | 4 | 0.6 |  |  | 18.4
4 | Rastreamento do transporte | Proposta | ILF | 15 | 2 | 1 | 2 | 7 | 5.5263 | 0.6 |  |  | 24.5053
Total |  |  |  | 88 | 6 | 2 | 9 | 31 | 16.9463 | 1.2 |  | 0 | 72.5853
DATA FUNCTIONS - CHANGED
Reference | User Story | Function Brief | FP Type | DET | RET | PET | LCS | IFPUG UFP | Progressive UFP | IPF | Reuse% | Reuse FP | Man Hours | DET Details | RET Details | PET Details | LCS Details | Reuse Details
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
DATA FUNCTIONS - DELETED
Reference | User Story | Function Brief | FP Type | DET | RET | PET | LCS | IFPUG UFP | Progressive UFP | IPF |  |  | Man Hours | DET Details | RET Details | PET Details | LCS Details
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRANSACTION FUNCTIONS - ADDED
Reference | User Story | Function Brief | Type | DET | RET | PET | LCS | IFPUG UFP | Progressive UFP | IPF | Reuse% | Reuse FP | Man Hours | DET Details | RET Details | PET Details | LCS Details | Reuse Details
2 | Aprovar Cotação | Freelancer | EI | 25 | 1 | 0 | 2 | 4 | 6.25 | 0 |  |  | 25
1 | Solicitar Cotação | Cliente | EI | 28 | 1 | 0 | 2 | 4 | 7 | 0 |  |  | 28
3 | Sistema de lançamento de coletas | Serviço | EO | 20 | 1 | 1 | 3 | 5 | 5 | 0.6 |  |  | 22.4
4 | Rastreamento do transporte | Proposta | EI | 15 | 1 | 1 | 2 | 3 | 3 | 0.6 |  |  | 14.4
Total |  |  |  | 88 | 4 | 2 | 9 | 16 | 21.25 | 1.2 |  | 0 | 89.8
TRANSACTION FUNCTIONS - CHANGED
Reference | User Story | Function Brief | Type | DET | RET | PET | LCS | IFPUG UFP | Progressive UFP | IPF | Reuse% | Reuse FP | Man Hours | DET Details | RET Details | PET Details | LCS Details | Reuse Details
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
TRANSACTION FUNCTIONS - DELETED
Reference | User Story | Function Brief | Type | DET | RET | PET | LCS | IFPUG UFP | Progressive UFP | IPF |  |  | Man Hours | DET Details | RET Details | PET Details | LCS Details
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
REUSE APPLICATION COMPONENTS
Reference | User Story | Function Brief | [9 empty] | Reuse FP | Man Hours
Total | [11 empty] | 0 | 0

## Helper (hidden)
Dropdown Contents |  |  |  | Currency
|  |  |  | Country | Currency | ISO-4217
| Data Types | Transaction Types | Conditional Clause | Afghanistan | Afghan afghani | AFN
| ILF | EI | Yes | Albania | Albanian lek | ALL
| EIF | EO | No | Algeria | Algerian dinar | DZD
|  | EQ |  | Andorra | European euro | EUR
|  |  |  | Angola | Angolan kwanza | AOA
| Currency |  |  | Anguilla | East Caribbean dollar | XCD
| Dollar |  |  | Antigua and Barbuda | East Caribbean dollar | XCD
| Pound |  |  | Argentina | Argentine peso | ARS
| Euro |  |  | Armenia | Armenian dram | AMD
| Ruble |  |  | Aruba | Aruban florin | AWG
| Rupee |  |  | Australia | Australian dollar | AUD
| Yen |  |  | Austria | European euro | EUR
|  |  |  | Azerbaijan | Azerbaijani manat | AZN
|  |  |  | Bahamas | Bahamian dollar | BSD
|  |  |  | Bahrain | Bahraini dinar | BHD
|  |  |  | Bangladesh | Bangladeshi taka | BDT
|  |  |  | Barbados | Barbadian dollar | BBD
|  |  |  | Belarus | Belarusian ruble | BYR
|  |  |  | Belgium | European euro | EUR
|  |  |  | Belize | Belize dollar | BZD
|  |  |  | Benin | West African CFA franc | XOF
|  |  |  | Bhutan | Bhutanese ngultrum | BTN
|  |  |  | Bolivia | Bolivian boliviano | BOB
|  |  |  | Bosnia-Herzegovina | Bosnia and Herzegovina konvertibilna marka | BAM
|  |  |  | Botswana | Botswana pula | BWP
|  |  |  | Brazil | Brazilian real | BRL
|  |  |  | Brunei | Brunei dollar | BND
|  |  |  | Bulgaria | Bulgarian lev | BGN
|  |  |  | Burkina Faso | West African CFA franc | XOF
|  |  |  | Burundi | Burundi franc | BIF
|  |  |  | Cambodia | Cambodian riel | KHR
|  |  |  | Cameroon | Central African CFA franc | XAF
|  |  |  | Canada | Canadian dollar | CAD
|  |  |  | Cape Verde | Cape Verdean escudo | CVE
|  |  |  | Cayman Islands | Cayman Islands dollar | KYD
|  |  |  | Central African Republic | Central African CFA franc | XAF
|  |  |  | Chad | Central African CFA franc | XAF
|  |  |  | Chile | Chilean peso | CLP
|  |  |  | China | Chinese renminbi | CNY
|  |  |  | Colombia | Colombian peso | COP
|  |  |  | Comoros | Comorian franc | KMF
|  |  |  | Congo | Central African CFA franc | XAF
|  |  |  | Congo, Democratic Republic | Congolese franc | CDF
|  |  |  | Costa Rica | Costa Rican colon | CRC
|  |  |  | Côte d'Ivoire | West African CFA franc | XOF
|  |  |  | Croatia | Croatian kuna | HRK
|  |  |  | Cuba | Cuban peso | CUC
|  |  |  | Cyprus | European euro | EUR
|  |  |  | Czech Republic | Czech koruna | CZK
|  |  |  | Denmark | Danish krone | DKK
|  |  |  | Djibouti | Djiboutian franc | DJF
|  |  |  | Dominica | East Caribbean dollar | XCD
|  |  |  | Dominican Republic | Dominican peso | DOP
|  |  |  | East Timor | uses the U.S. Dollar | USD
|  |  |  | Ecuador | uses the U.S. Dollar | USD
|  |  |  | Egypt | Egyptian pound | EGP
|  |  |  | El Salvador | uses the U.S. Dollar | USD
|  |  |  | Equatorial Guinea | Central African CFA franc | GQE
|  |  |  | Eritrea | Eritrean nakfa | ERN
|  |  |  | Estonia | Estonian kroon | EEK
|  |  |  | Ethiopia | Ethiopian birr | ETB
|  |  |  | Falkland Islands | Falkland Islands pound | FKP
|  |  |  | Fiji | Fijian dollar | FJD
|  |  |  | Finland | European euro | EUR
|  |  |  | France | European euro | EUR
|  |  |  | French Polynesia | CFP franc | XPF
|  |  |  | Gabon | Central African CFA franc | XAF
|  |  |  | Gambia | Gambian dalasi | GMD
|  |  |  | Georgia | Georgian lari | GEL
|  |  |  | Germany | European euro | EUR
|  |  |  | Ghana | Ghanaian cedi | GHS
|  |  |  | Gibraltar | Gibraltar pound | GIP
|  |  |  | Greece | European euro | EUR
|  |  |  | Grenada | East Caribbean dollar | XCD
|  |  |  | Guatemala | Guatemalan quetzal | GTQ
|  |  |  | Guinea | Guinean franc | GNF
|  |  |  | Guinea-Bissau | West African CFA franc | XOF
|  |  |  | Guyana | Guyanese dollar | GYD
|  |  |  | Haiti | Haitian gourde | HTG
|  |  |  | Honduras | Honduran lempira | HNL
|  |  |  | Hong Kong | Hong Kong dollar | HKD
|  |  |  | Hungary | Hungarian forint | HUF
|  |  |  | Iceland | Icelandic króna | ISK
|  |  |  | India | Indian rupee | INR
|  |  |  | Indonesia | Indonesian rupiah | IDR
|  |  |  | International Monetary Fund | Special Drawing Rights | XDR
|  |  |  | Iran | Iranian rial | IRR
|  |  |  | Iraq | Iraqi dinar | IQD
|  |  |  | Ireland | European euro | EUR
|  |  |  | Israel | Israeli new sheqel | ILS
|  |  |  | Italy | European euro | EUR
|  |  |  | Jamaica | Jamaican dollar | JMD
|  |  |  | Japan | Japanese yen | JPY
|  |  |  | Jordan | Jordanian dinar | JOD
|  |  |  | Kazakhstan | Kazakhstani tenge | KZT
|  |  |  | Kenya | Kenyan shilling | KES
|  |  |  | Kiribati | Australian dollar | AUD
|  |  |  | Korea North | North Korean won | KPW
|  |  |  | Korea South | South Korean won | KRW
|  |  |  | Kuwait | Kuwaiti dinar | KWD
|  |  |  | Kyrgyzstan | Kyrgyzstani som | KGS
|  |  |  | Laos | Lao kip | LAK
|  |  |  | Latvia | Latvian lats | LVL
|  |  |  | Lebanon | Lebanese lira | LBP
|  |  |  | Lesotho | Lesotho loti | LSL
|  |  |  | Liberia | Liberian dollar | LRD
|  |  |  | Libya | Libyan dinar | LYD
|  |  |  | Liechtenstein | uses the Swiss Franc | CHF
|  |  |  | Lithuania | Lithuanian litas | LTL
|  |  |  | Luxembourg | European euro | EUR
|  |  |  | Macau | Macanese pataca | MOP
|  |  |  | Macedonia (Former Yug. Rep.) | Macedonian denar | MKD
|  |  |  | Madagascar | Malagasy ariary | MGA
|  |  |  | Malawi | Malawian kwacha | MWK
|  |  |  | Malaysia | Malaysian ringgit | MYR
|  |  |  | Maldives | Maldivian rufiyaa | MVR
|  |  |  | Mali | West African CFA franc | XOF
|  |  |  | Malta | European Euro | EUR
|  |  |  | Mauritania | Mauritanian ouguiya | MRO
|  |  |  | Mauritius | Mauritian rupee | MUR
|  |  |  | Mexico | Mexican peso | MXN
|  |  |  | Micronesia | uses the U.S. Dollar | USD
|  |  |  | Moldova | Moldovan leu | MDL
|  |  |  | Monaco | European Euro | EUR
|  |  |  | Mongolia | Mongolian tugrik | MNT
|  |  |  | Montenegro | European Euro | EUR
|  |  |  | Montserrat | East Caribbean dollar | XCD
|  |  |  | Morocco | Moroccan dirham | MAD
|  |  |  | Mozambique | Mozambican metical | MZM
|  |  |  | Myanmar | Myanma kyat | MMK
|  |  |  | Namibia | Namibian dollar | NAD
|  |  |  | Nauru | Australian dollar | AUD
|  |  |  | Nepal | Nepalese rupee | NPR
|  |  |  | Netherlands Antilles | Netherlands Antillean gulden | ANG
|  |  |  | Netherlands | European euro | EUR
|  |  |  | New Caledonia | CFP franc | XPF
|  |  |  | New Zealand | New Zealand dollar | NZD
|  |  |  | Nicaragua | Nicaraguan cordoba | NIO
|  |  |  | Niger | West African CFA franc | XOF
|  |  |  | Nigeria | Nigerian naira | NGN
|  |  |  | Norway | Norwegian krone | NOK
|  |  |  | Oman | Omani rial | OMR
|  |  |  | Pakistan | Pakistani rupee | PKR
|  |  |  | Palau | uses the U.S. Dollar | USD
|  |  |  | Panama | Panamanian balboa | PAB
|  |  |  | Panama Canal Zone | uses the U.S. Dollar | USD
|  |  |  | Papua New Guinea | Papua New Guinean kina | PGK
|  |  |  | Paraguay | Paraguayan guarani | PYG
|  |  |  | Peru | Peruvian nuevo sol | PEN
|  |  |  | Philippines | Philippine peso | PHP
|  |  |  | Poland | Polish zloty | PLN
|  |  |  | Portugal | European euro | EUR
|  |  |  | Puerto Rico | uses the U.S. Dollar | USD
|  |  |  | Qatar | Qatari riyal | QAR
|  |  |  | Romania | Romanian leu | RON
|  |  |  | Russia | Russian ruble | RUB
|  |  |  | Rwanda | Rwandan franc | RWF
|  |  |  | Saint Helena | Saint Helena pound | SHP
|  |  |  | Saint Kitts and Nevis | East Caribbean dollar | XCD
|  |  |  | Saint Lucia | East Caribbean dollar | XCD
|  |  |  | Saint Vincent and the Grenadines | East Caribbean dollar | XCD
|  |  |  | Samoa (Western) | Samoan tala | WST
|  |  |  | San Marino | European euro | EUR
|  |  |  | Sao Tome and Principe | Sao Tome and Principe dobra | STD
|  |  |  | Saudi Arabia | Saudi riyal | SAR
|  |  |  | Senegal | West African CFA franc | XOF
|  |  |  | Serbia | Serbian dinar | RSD
|  |  |  | Seychelles | Seychellois rupee | SCR
|  |  |  | Sierra Leone | Sierra Leonean leone | SLL
|  |  |  | Singapore | Singapore dollar | SGD
|  |  |  | Slovakia | Slovak koruna | SKK
|  |  |  | Slovenia | European euro | EUR
|  |  |  | Solomon Islands | Solomon Islands dollar | SBD
|  |  |  | Somalia | Somali shilling | SOS
|  |  |  | South Africa | South African rand | ZAR
|  |  |  | South Sudan | Sudanese pound | SDG
|  |  |  | Spain | European euro | EUR
|  |  |  | Sri Lanka | Sri Lankan rupee | LKR
|  |  |  | Sudan | Sudanese pound | SDG
|  |  |  | Suriname | Surinamese dollar | SRD
|  |  |  | Swaziland | Swazi lilangeni | SZL
|  |  |  | Sweden | Swedish krona | SEK
|  |  |  | Switzerland | Swiss franc | CHF
|  |  |  | Syria | Syrian pound | SYP
|  |  |  | Taiwan | New Taiwan dollar | TWD
|  |  |  | Tajikistan | Tajikistani somoni | TJS
|  |  |  | Tanzania | Tanzanian shilling | TZS
|  |  |  | Thailand | Thai baht | THB
|  |  |  | Togo | West African CFA franc | XOF
|  |  |  | Tonga | Paanga | TOP
|  |  |  | Trinidad and Tobago | Trinidad and Tobago dollar | TTD
|  |  |  | Tunisia | Tunisian dinar | TND
|  |  |  | Turkey | Turkish new lira | TRY
|  |  |  | Turkmenistan | Turkmen manat | TMM
|  |  |  | Tuvalu | Australian dollar | AUD
|  |  |  | Uganda | Ugandan shilling | UGX
|  |  |  | Ukraine | Ukrainian hryvnia | UAH
|  |  |  | United Arab Emirates | UAE dirham | AED
|  |  |  | United Kingdom | British pound | GBP
|  |  |  | United States of America | United States dollar | USD
|  |  |  | Uruguay | Uruguayan peso | UYU
|  |  |  | Uzbekistan | Uzbekistani som | UZS
|  |  |  | Vanuatu | Vanuatu vatu | VUV
|  |  |  | Vatican | European euro | EUR
|  |  |  | Venezuela | Venezuelan bolivar | VEB
|  |  |  | Vietnam | Vietnamese dong | VND
|  |  |  | Wallis and Futuna Islands | CFP franc | XPF
|  |  |  | Yemen | Yemeni rial | YER
|  |  |  | Zambia | Zambian kwacha | ZMK
|  |  |  | Zimbabwe | Zimbabwean dollar | ZWD

## Relatórios Editáveis
Reference | User Story | Function Brief | Type | DET | RET | PET | LCS | IFPUG UFP | Progressive UFP | IPF | Reuse% | Reuse FP | Man Hours | DET Details | RET Details | PET Details | LCS Details | Reuse Details
2 | Aprovar Cotação | Freelancer | ILF | 25 | 1 | 0 | 2 | 7 | 3.5 | 0 |  |  | 14
2 | Aprovar Cotação | Freelancer | EI | 25 | 1 | 0 | 2 | 4 | 6.25 | 0 |  |  | 25
1 | Solicitar Cotação | Cliente | EI | 28 | 1 | 0 | 2 | 4 | 7 | 0 |  |  | 28
3 | Sistema de lançamento de coletas | Serviço | EO | 20 | 1 | 1 | 3 | 5 | 5 | 0.6 |  |  | 22.4
4 | Rastreamento do transporte | Proposta | EI | 15 | 1 | 1 | 2 | 3 | 3 | 0.6 |  |  | 14.4
1 | Solicitar Cotação | Cliente | ILF | 28 | 1 | 0 | 2 | 7 | 3.92 | 0 |  |  | 15.68
3 | Sistema de lançamento de coletas | Serviço | ILF | 20 | 2 | 1 | 3 | 10 | 4 | 0.6 |  |  | 18.4
4 | Rastreamento do transporte | Proposta | ILF | 15 | 2 | 1 | 2 | 7 | 5.5263 | 0.6 |  |  | 24.5053